## Business Requirements
[8 empty] | Applicable Brands |  |  | Applicable Devices |  | Applicable Pages
Requirement No. | Work Package | Included in the Integrations Work Package? | Functional Area | Functional Sub-Area | User Story | Acceptance Criteria & Associated Business Rules | Aspirational sites identified by Seafolly | Seafolly | Sunburn | Milea | Desktop & Tablet Landscape | Mobile & Tablet Portrait | Homepage | List pages (PLP, Search) | PDP - standalone product | PDP - product set | My Account | Store Locator | Mini-basket | Basket | Checkout | Hygiene pages | Existing Seafolly Functionality? Yes / No | Seafolly Prioritisation MoSCoW | Seafolly Business Driver for Custom Reqs (Commercial, Design, Legacy) | OOTB, TAS or Custom requirement? | Integration Required? | Effort Estimate | Effort Effort Rationale / Tryzens Comments | Proposed Phasing (based on Seafolly MoSCoWr ratings) | Tryzens Recommended Scope for Launch (updated 20/06/17) | Tryzens Recommended Scope - Rationale/Comments | Seafolly - Scope Review (in Vs Out)
SF-001 | Architecture |  | Architecture | Realms | As a business we want to operate a single realm to manage our Seafolly, Sunburn & Milea brands | - Seafolly, Sunburn and Milea will operate under a single realm - Maaji will operate under a separate 2nd realm |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-002 | Architecture |  | Architecture | Sites | As a business we want a Seafolly Australia site | - English language site - Transacts in AUD only (2 price books - List & Sale) |  | Y |  |  | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-003 | Architecture |  | Architecture | Sites | As a business we want a Seafolly USA site | - English language site - Transacts in USD (2 price books - List & Sale) |  | Y |  |  | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-004 | Architecture |  | Architecture | Sites | As a business we want a Seafolly Singapore site | - English language site - Transacts in SGD (2 price books - List & Sale) |  | Y |  |  | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-005 | Architecture |  | Architecture | Sites | As a business we want a Seafolly EU site | - German & English language sites - Transacts in EUR (2 price books - List & Sale) |  | Y |  |  | a | a | [10 empty] | No | Could Have / Wont Have |  | OOTB |  | n/a |  | Phase 2 | Out of Scope |  | Out
SF-006 | Architecture |  | Architecture | Sites | As a business we want a Sunburn Australia site | - English language site - Transacts in AUD (2 price books - List & Sale) |  |  | Y |  | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-007 | Architecture |  | Architecture | Sites | As a business we want a Milea Australia site | - English language site - Transacts in AUD (2 price books - List & Sale) |  |  |  | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | OOTB |  | n/a |  | Phase 2 | Out of Scope |  | Out
SF-008 | Architecture |  | Architecture | Catalogs | As a business we want separate storefront catalogs for each of the brands & sites | - 4 storefront catalogs identified for launch: = Seafolly AU = Seafolly US = Seafolly SG = Sunburn |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a | The assumption made here is that the PIM / middleware solution will provide the separate storefront product catalogs in the correct Salesforce format. However, if product catalogs cannot be provided in the correct format, this requirement will require some custom development and will therefore need to be re-estimated. | Launch | Launch |  | In
SF-008.1 | Architecture |  | Architecture | Catalogs | As a business we want separate storefront catalogs for each of the brands & sites | - 2 storefront catalogs identified for later phase: = Seafolly EU = Milea |  | Y | Y | Y | a | a | [10 empty] | Yes | Could Have / Wont Have |  | OOTB |  | n/a | The assumption made here is that the PIM / middleware solution will provide the separate storefront product catalogs in the correct Salesforce format. However, if product catalogs cannot be provided in the correct format, this requirement will require some custom development and will therefore need to be re-estimated. | Phase 2 | Out of Scope |  | Out
SF-009 | Architecture |  | Architecture | Content | As a business we want a private content library by brand | - Separate content libraries for Seafolly and Sunburn - Each brand will share the content library across all its domains (applies to Seafolly different sites) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-009.1 | Architecture |  | Architecture | Content | As a business we want a private content library for Milea | - Separate content library Milea |  | Y | Y | Y | a | a | [10 empty] | Yes | Could Have / Wont Have |  | OOTB |  | n/a |  | Phase 2 | Out of Scope |  | Out
SF-010 | Architecture |  | Architecture | Customer | As a business we want a single customer list per brand across all sites | - Single customer list across all Seafolly sites (AU, US, SG) - Single customer list for Sunburn |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a | The assumption made here is that the Magento customer data for the migration activity (required to create to these customer lists) will be provided by the PIM / middleware solution in the correct Salesforce format However, if the customer data cannot be provided in the correct format, this requirement will require some custom development and will therefore need to be re-estimated | Launch | Launch |  | In
SF-010.1 | Architecture |  | Architecture | Customer | As a business we want a single customer list per brand across all sites | - Single customer list across all Seafolly sites (existing sites + EU site) - Single customer list for Milea |  | Y | Y | Y | a | a | [10 empty] | Yes | Could Have / Wont Have |  | OOTB |  | n/a | The assumption made here is that the Magento customer data for the migration activity (required to create to these customer lists) will be provided by the PIM / middleware solution in the correct Salesforce format However, if the customer data cannot be provided in the correct format, this requirement will require some custom development and will therefore need to be re-estimated | Phase 2 | Out of Scope |  | Out
SF-011 | Architecture |  | Architecture | Localisation | As a business we want to allow a customer to switch the EU site language within a session | - Customer has the option to switch the site language between German and English |  | Y |  |  | a | a | [10 empty] | No | Could Have / Wont Have |  | OOTB |  | n/a | There is a dependency on the Seafolly team to ensure that the text from the dynamic and static resources is translated into all applicable languages | Phase 2 | Out of Scope |  | Out
SF-012 | Architecture |  | Architecture | Localisation | As a business we want the Seafolly EU site to have pricebook & language localisation by EU country | - The EU site supports a different language per EU country (i.e. locale) - The EU site supports a different pricebook per EU country (i.e. locale) - The specific requirements for this are still TBD (i.e. which locales, languages & pricebooks are required) |  | Y |  |  | a | a | [10 empty] | No | Could Have / Wont Have | Commercial | Custom |  | Medium | This is a high level estimate and is a subject to change based on the final requirement. | Phase 2 | Out of Scope |  | Out
SF-013 | Architecture |  | Architecture | Shipping | As a business we want shipping countries restrictions to be configurable by site | - Seafolly AU ships to AU and NZ - Seafolly US ships to US - Seafolly SG ships to SG - Sunburn AU ships to AU and NZ |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small | If new shipping countries are added that require changes to the front-end (e.g. specific checkout fields to be surfaced / validated etc.) then further customisations may be required and this would increase the effort estimate of this requirement to either medium or greater depending on the specific requirements | Launch | Launch |  | In
SF-013.1 | Architecture |  | Architecture | Shipping | As a business we want shipping countries restrictions to be configurable by site | - Seafolly US ships to existing countries + Canada - Seafolly EU shipping countries are TBA - Milea AU ships to AU & NZ |  | Y | Y | Y | a | a | [10 empty] | Yes | Could Have / Wont Have | Commercial | Custom |  | Small | If new shipping countries are added that require changes to the front-end (e.g. specific checkout fields to be surfaced / validated etc.) then further customisations may be required and this would increase the effort estimate of this requirement to either medium or greater depending on the specific requirements | Phase 2 | Out of Scope |  | Out
SF-014 | Integrations | Yes | Integrations | Customer | As a business we want a single view of customer across all channels within each brand | - Customer records should be synced between the ecomm platform and ERP/CRM application |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Commercial | TAS |  | n/a | The customer data format must be confirmed with Seafolly and Fusion Factory. Tryzens recommendation is that sensitive data should be skipped during export. | Launch | Launch |  | In
SF-015 | Integrations | Yes | Integrations | Monitoring | As a business we want to see if an order has not been received by the Seafolly backend system(s) | - The ecomm platform will highlight if an order has not reached the SFTP server - Any monitoring / error handling beyond this will be managed by the middleware |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Legacy | n/a |  | n/a | It would be part of the Managed Service contract that Tryzens offer. NOTE: there should also be some error handling & monitoring provided by the PIM / middleware solution | Launch | Launch |  | In
SF-016 | Product Enrichment & Pricing |  | Pricing | Promotions | As a business we want multi-buy discount values to be split proportionally across all applicable products within the order so that margins are accurate | - Multi-buy discount value to be split proportionally based on current selling price i.e. higher value items have more discount value apportioned to them, e.g. Item 1 = $60, Item 2 = $40 Multi-buy discount value (saving) = $10 across both items Discount value should be split out as $6 discount for item 1 and $4 discount for item 2 |  | Y | Y | Y | a | a | [11 empty] | Could Have / Wont Have | Legacy | Custom |  | Large | Due to the complexity of this requirement, Tryzens recommend that it is not implemented, and that Seafolly use % off or $ off promotions instead as a workaround (rather than using multi-buy promotions) | Phase 2 | Out of Scope |  | Out
SF-017 | Product Enrichment & Pricing |  | Product Enrichment | Images | As a business we want an easy way to manage product images | - Product images will be managed via the PIM / middleware solution - Salesforce DIS would be integrated for management of the product images on the storefront |  | Y | Y | Y | a | a | [10 empty] | No | Must Have | Legacy | TAS |  | n/a | The PIM wil be repsonsible for storing & providing the images (high res images) with Salesforce DIS being used to convert the images into the correct view type & resolution e.g: large images = 600px x 600px medium images = 300px x 300px small images = 150px x 150px etc. | Launch | Launch |  | In
SF-018 | Search & Browse | Yes | Browse | Blog | As a business we want to surface a blog on the website | - The ecomm platform will be integrated with WordPress - The blog link in the navigation will navigate to a standalone WordPress site |  | Y |  | Y | a | a | x | x | x | x |  |  |  | x |  | x | Yes | Could Have / Wont Have | Legacy | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-019 | Search & Browse |  | Browse | Footer | As a business we want a customisable footer | - The footer will contain 1 Content Slot and 4 Content Assets - A business user will manage the Content Slots/Assets that display in footer within the Business Manager |  | Y | Y | Y | a | a | x | x | x | x |  |  |  | x |  | x |  | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-020 | Search & Browse |  | Browse | Footer | As a business we want a sticky footer on the mobile site | - Specific requirements are TBC - further analysis needed |  | Y | Y | Y |  | a | x | x | x | x |  |  |  | x |  | x | No | Could Have / Wont Have | Design | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-021 | Search & Browse |  | Browse | Header | As a business we want a sticky header on the mobile site | - Specific requirements are TBC - further analysis needed |  | Y | Y | Y |  | a | x | x | x | x |  |  |  | x |  | x | No | Could Have / Wont Have | Design | Custom |  | Small | This estimate is based on the assumption that the customisation done for Jones Bootmaker would be implemented. If a more simplistic approach is required (i.e. the customisation done for TM Lewin) then the effort could be smaller) | Phase 2 | Out of Scope |  | Out
SF-022 | Search & Browse |  | Browse | Header | As a business we want a static content spot in the header so that we can surface a text based message to customers (e.g. free delivery |  |  | Y | Y | Y | a | a | x | x | x | x |  |  |  | x |  | x | No | Should Have |  | OOTB |  | n/a |  | Launch - TBC | Launch |  | In
SF-022.1 | Search & Browse |  | Browse | Header | As a business we want a rotating content spot in the header so that we can surface a text based message to customers (e.g. free delivery |  |  | Y | Y | Y | a | a | x | x | x | x |  |  |  | x |  | x | No | Could Have / Wont Have |  | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-023 | Search & Browse |  | Browse | Hidden Categories | As a business we want the ability to stop products within a hidden category from appearing within other categories | - Products within hidden categories do not appear within other categories |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | n/a |  | n/a | This should be handled by the PIM when producing the product catalogs - products in hidden categories should be removed from other categories within the PIM | Launch | Launch |  | In
SF-024 | Search & Browse |  | Browse | Homepage | As a business we want additional rendering template(s) for content management | -Specific requirements are TBD - based on wireframes & page design review by Seafolly team & in-house skill-set dependencies |  | Y | Y | Y | a | a | x | [10 empty] | Must Have | Design | Custom |  | Small | The estimate is based on 1 additional rendering template - if multiple templates are required, then the effort estimate will be greater. To provide a more accurate estimate, Seafolly will need to specifiy how many different homepage layouts would exist - Tryzens can then advise how many templates are needed and can re-estimate the effort to deliver this requirement. | Launch | Out of Scope | As Seafolly have a front-end developer in house, this person could manage the different homepage layouts using the OOTB rendering templates; therefore additional templates would not be required | Out
SF-025 | Search & Browse |  | Browse | Homepage | As a business we want to show videos on the homepage |  |  | Y | Y | Y | a | a | x | [9 empty] | Yes | Must Have |  | Custom |  | Small | This estimate is based on the assumption that videos would be embedded from external sources. Salesforce do not recommend hosting videos on their servers. | Launch | Out of Scope |  | Out
SF-026 | Search & Browse |  | Browse | Homepage | As a business we want a store locator function that is both icon and text based | - On desktop, the store locator icon is header with right adjacent text stating 'Find A Store' - On mobile, the store locator icon in within the burger menu with right adjacent text stating 'Find A Store' |  | Y | Y | Y | a | a | x | x | x | x |  |  |  | x |  | x | Yes | Must Have |  | Custom |  | Small |  | Launch | Launch |  | In
SF-027 | Search & Browse |  | Browse | Homepage | As a business we want a site selector in the header to allow customers to change site | - Site selector is both a country flag and currency text e.g. AUD, USD, SGD - EU flag and locale selection (e.g. Germany, France, UK etc.) is still TBC pending a business decision on how the EU site should operate |  | Y |  |  | a | a | x | x | x | x |  |  |  | x |  | x | Yes | Must Have |  | Custom |  | Small |  | Launch | Launch |  | In
SF-028 | Search & Browse |  | Browse | My Account | As a business we want wish list to be accessible from My Account (not the header) | - Wish list will be accessible through My Account; there will be no icon in the header - The wish list icon will also not show on the 'Add to Wish list' button on the PDP (this will be text only) |  | Y | Y | Y | a | a | x | x | x | x |  |  |  | x |  | x | No | Must Have | Design | OOTB |  | n/a |  | Launch | Launch |  | In
SF-029 | Search & Browse |  | Browse | My Account | As a business we want the account log-in functionality on mobile to surface within both the header and the burger menu | - Account log-in icon is surfaced within the mobile header - Account log-in icon is surfaced within the mobile burger menu - Selecting the account log-in icon from either the mobile header or mobile burger menu should navigate to the My Account landing page (where a customer can log in or create a new account) |  | Y | Y | Y |  | a | x | x | x | x |  |  |  | x |  | x | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-030 | Search & Browse |  | Browse | Navigation | As business we want a desktop navigation menu that opens on hover (and not on click) | - Desktop navigation menu opens on hover |  | Y | Y | Y | a |  | x | x | x | x |  |  |  | x |  | x | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-031 | Search & Browse |  | Browse | Navigation | As business we want a mobile navigation menu that opens on tap | - Mobile navigation menu opens on tap - Mobile navigation menu closes on tap |  | Y | Y | Y |  | a | x | x | x | x |  |  |  | x |  | x | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-032 | Search & Browse |  | Browse | Navigation | As a business we want the ability to make SALE products only appear within a SALE category and be excluded from all other categories | - Products within the SALE category do not appear within other categories |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | n/a |  | n/a | This should be handled by the PIM when producing the product catalogs - products in the SALE category should be removed from other categories within the PIM | Launch | Launch |  | In
SF-033 | Search & Browse |  | Browse | Navigation | As a customer, I want the ability to shop the site by 'Collection' either through the storefront navigation or through the list page filters | - This would be a middleware/PIM requirement to create a category & a variation group to achieve this - 'Collection' could be pattern, print, fabric etc. |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | n/a |  | n/a | This should be handled by the PIM when producing the product catalogs | Launch | Launch |  | In
SF-034 | Search & Browse |  | Browse | Navigation | As a business we want to show products as both standalone items (i.e. bikini tops, bikini bottoms) and as product sets (i.e. whole bikini) on the PLP and PDP so that a customer has the option to shop the site as they prefer | - This would be a middleware/PIM requirement: = categories must be created for the standalone items (i.e. Tops, Bottoms) and product sets must be defined = Standalone items will be displayed on the PLP and PDP when navigating from the main nav = Product sets will be displayed under 'Collection' or 'Shop the Look' categories within the main nav = Standalone items will have the product set as a alternative image on the PDP |  | Y |  |  | a | a | [10 empty] | No | Must Have |  | n/a |  | n/a | This should be handled by the PIM when producing the product catalogs. If the PIM cannot provide the product set within the product catalog, then the set can be manaully configured within the Business Manager tool and assigned to the relevant navigation category | Launch | Launch |  | In
SF-035 | Search & Browse |  | Browse | Navigation | As a business we want the mobile burger menu to shift the homepage to the right when opened | - When selected to open, the mobile burger menu should shift the homepage to the right - When selecting the mobile burger menu to close it, the action should shift the homepage back to its original position - The mobile burger menu when opened should be wider than the SiteGenesis design |  | Y | Y | Y |  | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope | OOTB SiteGeneis already provides some degree of right-hand shift when opening the burger menu; propose that this is acceptable for launch and widened at a later date | Out
SF-036 | Search & Browse |  | Browse | Navigation | As a customer I want to be able to navigate to a brand directory from the main nav on the Sunburn site | - Customers can navigate to the brands directory page from the main nav - This is as per the Jones site | Jones Bootmaker |  | Y |  | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | The brands category/sub-cats must be provided by the PIM in the catalog import. The estimate is based on the current layout of the Sunburn site | Launch | Out of Scope |  | In
SF-037 | Search & Browse |  | Browse | Navigation | As a customer I want to be able to navigate to a brand landing page or list page from the brand directory page | - Brands are displayed as a hyperlink on the brands directory page - Selecting the hyperlink navigates to the individual brand landing/category/list page - This is as per the Jones site | Jones Bootmaker |  | Y |  | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | The brands category/sub-cats must be provided by the PIM in the catalog import. The estimate is based on the assumption that the customisation done for Jones Bootmaker would be implemented: https://www.jonesbootmaker.com/brands | Launch | Out of Scope |  | In
SF-038 | Search & Browse |  | Browse | Shoppable Instagram | As a business we want a content page to surface shoppable Instagram images on the site | - Shoppable Instagram content will be surfaced on a static content page - Content page will surface a single content spot with a grid layout rendering template |  | Y |  |  | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small | Estimate based on a custom Salesforce solution (not an integration via FourSixty) Instagram images will need to be provided as part of the Master Catalog. | Launch | Out of Scope | Proposal for launch is to integrate with FourSixty to continue the AS-IS process for surfacing shoppable instagram on the site (see req #SF-38.1); a custom solution would be considered for a later phase | Out
SF-038.1 | Search & Browse |  | Browse | Shoppable Instagram | As a business we want to surface shoppable instagram content on the website | - The ecomm platform will be intgrated with FourSixty to surface shoppable instagram content - Products and instagram images association will be managed within the FourSixty application - Business rules re: which instragam images are shown and in which order will be managed with thin the FourSixty application |  | Y |  |  | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small | Estimate based on delivering the AS-IS shoppable instagram solution via an integration with Foursixty (not a custom solution on Salesforce) | Launch | Out of Scope | Marked as OOS following Seafolly review | Out
SF-039 | Search & Browse |  | Browse | Shoppable Instagram | As a business we want each Instagram image within the grid layout to navigate to a specific PDP when selected by the customer | - Images within the content spot grid will navigate straight to the relevant product / product set PDP (the AS-IS functionality where a pop-up is surfaced before a customer can navigate to a PDP will not be replicated) |  | Y |  |  | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small | Estimate based on a custom Salesforce solution (not an integration via FourSixty) Will require manual configuration within the Business Manager tool | Launch | Out of Scope | Proposal for launch is to integrate with FourSixty to continue the AS-IS process for surfacing shoppable instagram on the site (see req #SF-38.1); a custom solution would be considered for a later phase | Out
SF-040 | Search & Browse |  | Browse | Shoppable Instagram | As a business we want the ability to configure which product / product set Instagram images are surfaced within the content spot grid | - A business user will specify a list of products / product sets that will be rendered in the content spot |  | Y |  |  | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a | The product IDs would be listed in a Content Slot with "Product" type slot configuration. Will require manual configuration within the Business Manager tool | Launch | Out of Scope | Proposal for launch is to integrate with FourSixty to continue the AS-IS process for surfacing shoppable instagram on the site (see req #SF-38.1); a custom solution would be considered for a later phase | In
SF-041 | Search & Browse |  | Browse | Shoppable Instagram | As a business we want to be able to configure a product / product set against each Instagram image | - Business user will manually associate an Instagram image with a product / product set through Business Manager - A business user will be able to associate a maximum of 5 Instagram images against a single product / product set |  | Y |  |  | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Small | Estimate based on a custom Salesforce solution (not an integration via FourSixty) Will require manual configuration within the Business Manager tool | Launch | Out of Scope | Proposal for launch is to integrate with FourSixty to continue the AS-IS process for surfacing shoppable instagram on the site (see req #SF-38.1); a custom solution would be considered for a later phase | Out
SF-042 | Search & Browse |  | Browse | Shoppable Instagram | As a business we want to be able to specify the order in which Instagram images appear within the content spot grid if more than 1 image is associated with a product / product set | - Where >1 image is associated with a product / product set, a business user can specify where those images are surfaced on the content spot grid and in which order e.g. Product A has 3 Instagram images associated - image 1 is surfaced in position 2 on the grid, image 2 is surfaced in position 10 on the grid, image 3 is surface in position 5 on the grid |  | Y |  |  | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small | Estimate based on a custom Salesforce solution (not an integration via FourSixty) Will require manual configuration within the Business Manager tool | Launch | Out of Scope | Proposal for launch is to integrate with FourSixty to continue the AS-IS process for surfacing shoppable instagram on the site (see req #SF-38.1); a custom solution would be considered for a later phase | Out
SF-043 | Search & Browse |  | Browse | Shoppable Instagram | As a business we want to show the Instagram image(s) as an alternative image on the PDP | - Instagram image(s) will appear as alternative images on the PDP - These images will not be shoppable content (as they are already on the relevant product / product set PDP) |  | Y |  |  | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Medium | The estimate is subject to change based on the final designs. | Phase 2 | Out of Scope |  | Out
SF-044 | Search & Browse | Yes | Browse | Store Locator | As a customer I want to access to a store locator function | - The ecomm platform will be integrated with Google Maps - The store locator functionality will as per the Whistles customisation - Additional customisation is for each store type (e.g. Seafolly, Sunburn, Milea) to have a different colour pin on the store map | Whistles | Y | Y | Y | a | a | [10 empty] | No | Must Have | Commercial | Custom |  | Small | The estimate is based on delivering the Whistles customisations on top of the TAS functonality (hence a reduced effort from previous BRD submissions), however is subject to change based on the final designs. Store data must be provided via the PIM (this data is currently not part of the Fusion Factory cartridge and so requires development on both the front & back-end systems) Need confirmation on whether all stores should be displayed on all sites (e.g. Seafolly site to show Seafolly, Sunburn & Milea stores etc.) | Launch | Out of Scope | Propose that the TAS store locator is implemented for launch instead - please refer to req #SF-044.1 | In
SF-044.1 | Search & Browse | Yes | Browse | Store Locator | As a customer I want to access to a store locator function |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have | Commercial | TAS |  | n/a | This will be based on the TAS store locator functionality which can be viewed here: http://2020tech05.tech-prtnr-eu01.dw.demandware.net/on/demandware.store/Sites-Showcase-Site/en/StoreFinder-Show The TAS version does not contain the following customisations that are included in the Whistles store locator: - Store pins customisations - Styling Store data must be provided via the PIM (this data is currently not part of the Fusion Factory cartridge and so requires development on back-end systems) | Launch | Launch |  | In
SF-045 | Search & Browse |  | Browse | Store Locator | As a customer, I want to be able to search for stores by specific attributes | - A customer will be able to filter a list of stores by store type e.g. Seafolly store, Sunburn stores and Seafolly stockists - A customer will be able to filter a list of stores by collection e.g. Seafolly or Seafolly Girls |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | TAS |  | n/a | The assumption is that store type and collection attributes will be part of the stores feed, which would be in a standard SCC format, and will be generated by MW. | Launch - TBC | Launch |  | In
SF-046 | Search & Browse |  | Browse | Store Stock Look-up | As a customer, I want to be able to check stock in store for any product from the PDP | - The store stock look-up will be as per the Whistles customisation - Inventory list per store will be provided by the PIM - A "check stock in store" link will be surfaced on the PDP as per the Whistles PDP design | Whistles | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Commercial | Custom |  | Medium | An inventory list per store must be provided by the PIM/middleware | Phase 2 | Out of Scope |  | Out
SF-047 | Search & Browse |  | PDP | AfterPay | As a business we want to surface AfterPay instalment payment information on the PDP | - AfterPay information should only be surfaced on AU sites - AfterPay information to show under the Was/Now/Promo icons on the PDP |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small |  | Launch | Launch |  | In
SF-048 | Search & Browse |  | PDP | AfterPay | As a business we want the number of AfterPay instalments and payment amount due at each instalment to be calculated and surfaced on each PDP | - The messaging should include the number of instalments and payment due at each instalment |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small |  | Launch | Launch |  | In
SF-049 | Search & Browse |  | PDP | Attributes | As a business we want to show product information on the PDP using an accordion display | - The following 5 components should display on the PDP (design dependent): Description, Size & Fit, Fabric Care, Delivery & Returns, Ratings & Reviews - The default behaviour for the accordion is to be closed - Only one accordion can be open at any time - opening one accordion will close the previously opened one - Accordion open/close will be animated (as per Whistles functionality) - Accordion displays under the 'Add to Bag' button for each product within the product set | Avenue32, Whistles | Y | Y | Y | a | a | [10 empty] | No | Must Have | Commercial | Custom |  | Small | These attributes should be provided by the PIM when producing the product catalogs | Launch | Launch |  | In
SF-050 | Search & Browse |  | PDP | Colours | As a business we want to display the different colour variants for a product as colour swatches on the PDP | - The PDP image defaults to the colour swatch chosen |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-051 | Search & Browse |  | PDP | Colours | As a business we want to replace the "Select Colour" wording on the PDP with the name of the chosen colour swatch | - The PDP will not display the wording 'Select Colour'; - The placement of the colour name (when a swatch is chosen) should moved to where 'Select Colour' appears (as per the SiteGenesis layout) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Design | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-052 | Search & Browse |  | PDP | Content | As a business we want a content spot to surface on the PDP under the product information so that we can display content regarding fit and flatter |  | G-Star Raw | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Commercial | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-053 | Search & Browse |  | PDP | Images | As a business we want the product zoom pop up image to surface over the PDP images | - Product zoom pop up box surfaces over PDP images, and not over the variant selections - This is as per the Avenue32 and Jones Bootmaker functionality | Avenue32, Jones Bootmaker | Y | Y | Y | a | [11 empty] | No | Should Have | Design | Custom |  | Small |  | Launch - TBC | Out of Scope |  | In
SF-054 | Search & Browse |  | PDP | Images | As a business we want the alternative product images on the PDP to surface on the left of the main PDP image | As per Avenue32 desktop |  | Y | Y | Y | a | [11 empty] | No | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | In
SF-055 | Search & Browse |  | PDP | Images | As a business we want scrolling callouts to show on the PDP image to highlight to a customer that additional images exist & that scrolling is possible | - On desktop, arrows should be surfaced on either side of the image (as per Avenue32 functionality) - On mobile, dots should show on the image - the number of dots surfaced indicates the number of available images - On mobile the relevant dot is highlighted when scrolling to the next image | Avenue32, ASOS, Topshop | Y | Y | Y | a | a | [10 empty] | Yes | Should Have | Design | Custom |  | Small |  | Launch - TBC | Out of Scope |  | In
SF-056 | Search & Browse |  | PDP | Mix & Match | As a business we want to show 'mix & match' options on the PDP where multiple product set combinations exist, so that we can maximise conversion on bikini tops & bottoms | - Specific requirements are TBC - further analysis needed | O'Neill | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Commercial | Custom |  | Large | This is a very high level estimate only (based on the O'Neill example) and the effort estimate may increase once specific requirements are known | Phase 2 | Out of Scope |  | Out
SF-057 | Search & Browse |  | PDP | Pre-Order | As a customer, I want to be able to pre-order an new product | - Specific requirements are TBC - further analysis needed (however, some basic functionality is OOTB). Currently this is offered to customers, but is managed manually by Seafolly |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | OOTB |  | n/a | This is based on the assumption that the OOTB pre-order functionality will be implemented (& supported by the back-end systems). If customisations are required, then this requirement will need to be re-estimated | Phase 2 | Out of Scope |  | Out
SF-058 | Search & Browse |  | PDP | Pricing | As a business we want to show Was/Now pricing on the PDP | - PDP shows original & markdown price (if a MD price is applicable) - PDP shows original (list price) and any applicable markdown price adjacent to it - PDP does not show a % off |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-059 | Search & Browse |  | PLP | Pricing | As a business we want to show Was/Now pricing on the PLP product tiles | - PLP product tile shows original & markdown price (if a MD price is applicable) - PLP product tile does not show a % off |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-060 | Search & Browse |  | PDP | Pricing | As a business we want to show Was/Now pricing on the product tiles displayed within recommendation content spots | - The product tile within the recommendations content spot shows original & markdown price (if a MD price is applicable) - The product tile within the recommendations content spot does not show a % off |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-061 | Search & Browse |  | PDP | Promotions | As a business we want to display a promotional icon on the PDP to highlight where a product is on promotion | - if there is an applicable promotional price, a promo icon is displayed on The PDP - Promotional icon look & feel will be design dependent - Promo icon and name will display in line with the Was/Now prices on desktop PDP - Promo icon and name will display under the Was/Now prices on mobile PDP - The promotion name should be surfaced adjacent to the promotional icon (e.g. 10% off all tops) - The promotional callout (as per the SiteGenesis OOTB layout) is not surfaced |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Commercial | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-062 | Search & Browse |  | PDP | Promotions | As a business we do not want to display the promotional price on the PDP | - Promotional price will not be surfaced on the PDP. The PDP will only show the List price or the Was/Now price if a sale pricebook exists - Promotional price will only show on the mini-basket, basket and checkout pages |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Design | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-063 | Search & Browse |  | PDP | Ratings & Reviews | As a business we want to offer ratings & reviews on the PDP | - Specific requirements are TBC - further analysis needed and a decision made on the 3rd party provider |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Commercial | Custom |  | Medium | This estimate is based on the assumption that a 3rd party tool with a cartridge is implemented. | Phase 2 | Out of Scope |  | Out
SF-064 | Search & Browse |  | PDP | Ratings & Reviews | As a business we want to show the average star rating (from ratings & reviews) under the product name on the PDP | - The ecomm platform will be integrated with a ratings and reviews too - Look & feel of the stars will be design dependent - These will not be surfaced on a product set PDP |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-065 | Search & Browse |  | PDP | Recommendations | As a business we want to surface a 'Complete the Look' recommendation on the PDP | - As per the Avenue32 PDP design - This will be a vertical carousel | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | OOTB |  | n/a |  | Launch | Out of Scope | Propose that this is descoped as even though the vertical carousel is OOTB, it is increased custom effort to style a vertical carousel | Out
SF-066 | Search & Browse |  | PDP | Recommendations | As a business we want to easily configure products that display a "Complete the Look" recommendation on the PDP | - This type of recommendation will be an explicit (manual) recommendation and the product associations will be managed within the PIM - If viewing a bikini top, this will be the matching bottoms options (and vice versa). - If viewing a standalone product (i.e. a one piece swimsuit) this will be the matching accessories for the item | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a | The recommendation must be configured in the PIM | Launch | Out of Scope | Propose that this is descoped as even though the vertical carousel is OOTB, it is increased custom effort to style a vertical carousel | In
SF-067 | Search & Browse |  | PDP | Recommendations | As a business we want to switch the PDP "Complete the look" recommendation on/off | - The recommendation can be switched on/off i.e. show or not show on the PDP | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-068 | Search & Browse |  | PDP | Recommendations | As a business we want to surface a 'You May Also Like' recommendation on the PDP | - As per the Avenue32 PDP design - This will be a horizontal carousel | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-069 | Search & Browse |  | PDP | Recommendations | As a business we want to easily configure products that display a "You May Also Like" recommendation on the PDP | - This will be an Einstein- generated implicit recommendation - However until Einstein recommendations are accurate, this type of recommendation will be an explicit (manual) recommendation | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-070 | Search & Browse |  | PDP | Recommendations | As a business we want to switch the PDP "You May Also Like" recommendation on/off | - The recommendation can be switched on/off i.e. show or not show on the PDP | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-071 | Search & Browse |  | PDP | Recommendations | As a business we want to surface a 'Recently Viewed' recommendation on the PDP | - This will be based on last viewed items within that session - This will not display until populated with items - This will be a horizontal carousel | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-072 | Search & Browse |  | PDP | Recommendations | As a business we want to switch the PDP "Recently Viewed" recommendation on/off | - The recommendation can be switched on/off i.e. show or not show on the PDP | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-073 | Search & Browse |  | PDP | Recommendations | As a business we want to surface the "You May Also Like" and "Recently Viewed" carousels in the same container on the PDP | - As per the Avenue32 PDP design - Both carousels display in the same container underneath the product image & details - If one carousel is not displayed (e.g. "Recently Viewed" because the customer has not looked at any products yet), the other carousel will fill the container - Each carousel can be expanded to show more products - this will surface a tabbed view of each carousel | [16 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-074 | Search & Browse |  | PDP | Recommendations | As a business we want all recommendation carousels to be styled according to brand guidelines | - Styling / look & feel of all carousels will be design dependent |  | Y | Y | Y | a | a | [10 empty] | No | Must Have | Design | Custom |  | Small | Seafolly to review PDP layout and make a descision on which recommendation carousels are surfaced and where. Seafolly also to review the SiteGenesis OOTB (horizontal) carousels styling and a make a descision on whether the OOTB or Avenue32 stlying is preferred - the effort estimate for this requirement is for horizontal carousel styling only; if vertical carousels are in scope, then the effort will increase. Tryzens to provide initial plans and costs based on the requirement as-is | Launch | Launch |  | In
SF-075 | Search & Browse |  | PDP | Sizing | As a business we want the size variant selection on the PDP to be a drop down selection filter | - This should utilise the native drop down filter functionality within desktop, tablet & mobile | Adidas | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Design | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-076 | Search & Browse |  | PDP | Sizing | As a business we want to highlight stock availability against each size within the size variant drop down filter | - if a size variant is OOS, then the size still appears within the drop down filter, however the size value is struck through and cannot be selected by the user - If a size variant is in stock, the size value is available to select |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Commercial | Custom |  | Small | If the restriction re: not letting a customer select an OOS size is removed from this requirement, then the requirement becomes OOTB and there is no customisation effort required | Launch | Out of Scope |  | Out
SF-077 | Search & Browse |  | PDP | Sizing | As a business we want to be able to surface site-specific sizing display names | - On the AU site, size will be displayed as "8 AU" - On the US site, site will be displayed as "4 US / 8 AU" |  | Y |  |  | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a | The size variant display name should be handled by the PIM when producing the product catalogs | Launch | Launch |  | In
SF-078 | Search & Browse |  | PDP | Sizing | As a business we want to be able to easily manage country specific size mapping | - This would be a middleware/PIM requirement |  | Y |  |  | a | a | [10 empty] | Yes | Must Have |  | n/a |  | n/a | The country-specific size mapping should be handled by the PIM when producing the product catalogs | Launch | Launch |  | In
SF-079 | Search & Browse |  | PDP | Sizing | As a business we want the PDP size guide link to surface near to the size drop down filter | - Size guide link should display next to size drop down filter on desktop - Size guide link should display above size drop down filter on mobile |  | Y | Y | Y | a | a | [10 empty] | No | Must Have | Design | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-080 | Search & Browse |  | PDP | Sizing | As a business we want the PDP size guide to surface as a pop-up on the PDP when selected by the customer |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | in
SF-081 | Search & Browse |  | PDP | Social Sharing | As a business we want to display social sharing icons on the PDP | - Social sharing icons should be surfaced on the PDP as per the Avenue32 PDP design - On a Product Set PDP, there should only be a single instance of the social sharing icons for the whole set (i.e. not one per product set item) |  | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | OOTB |  | n/a |  | Launch - TBC | Launch |  | in
SF-082 | Search & Browse |  | PDP | Social Sharing | As a business we don’t want to offer Google+ as a social sharing option | - Google+ icon should not display within the social sharing icons on the PDP |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have | Design | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-083 | Search & Browse |  | PDP | Social Sharing | As a business we want a content spot surfaced above the social sharing icons on the PDP so that we can display a message to the customer | - This is as per the Avenue32 PDP design |  | Y | Y | Y | a | a | [10 empty] | Yes | Could Have / Wont Have | Design | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-084 | Search & Browse |  | PDP | Store Stock Look-up | As a business we want the Store Stock Locator to be surfaced in line the 'Add to Wish list' button | - Store icon should be surfaced adjacent to text - Store icon should be the same colour as the store pins shown within the store locator pages (each brand [SF, SB, ML] will have different colour store pin) | Whistles | Y | Y | Y | a | [11 empty] | No | Could Have / Wont Have | Design | Custom |  | Small | Please refer to the TM Lewin AU site to view the store locator functionality with different colour pins per store type | Phase 2 | Out of Scope |  | Out
SF-085 | Search & Browse |  | PDP | PDP | As a business we want the 'Add to Bag' and 'Add to Wish list' buttons on the PDP to be stacked above each other | - This will be as per the Avenue32 PDP design - Applies to both desktop & mobile sites | Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Must Have | Design | Custom |  | Small |  | Launch | Launch |  | In
SF-086 | Search & Browse |  | PDP | PDP | As a business we want to remove the quantity field on the PDP | - Quantity field is not surfaced - A customer can only add 1 unit of the product to their bag at a time - if multiple quantities of the same SKU are required, they will be added to the bag individually |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Design | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-087 | Search & Browse |  | PDP | PDP | As a customer I want clear messaging on the PDP to advise me that I need to select variants before trying to add the product to the bag | - This is as per the Avenue32 functionality - Message will only be surfaced if a customer selects 'add to bag' without selecting all applicable variants - Message text will be design dependent (example text to be "Please select a size to add to your bag." |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Design | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-088 | Search & Browse |  | PDP | PDP | As a business we don’t want to surface Previous/Next scrolling icons on the PDP for other items within the list page | - Previous/Next icons are not surfaced on the PDP - A customer cannot scroll to the next item in the list page from the PDP |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Design | TAS |  | n/a |  | Launch | Launch |  | In
SF-089 | Search & Browse |  | PDP | PDP | As a business we want SKU number to surface under the product name |  |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-090 | Search & Browse |  | PDP | PDP | As a business we want to surface brand name above product name on the PDP | - Applies to Sunburn site only - Selecting the brand name on the PDP navigates to PLP for that brand |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Design | Custom |  | Small | This should be provided by the PIM when producing the product catalogs | Launch | Launch |  | In
SF-091 | Search & Browse |  | PDP - Product Sets | Attributes | As a business we want the product set PDP to surface only the Description and Fit & Size accordion against each product within the product set | - Fabric Care, Delivery & Returns, Ratings & Reviews should not be surfaced - Accordion behaviour is the same as the standalone product PDP accordion behaviour - Accordion displays under the 'Add to Bag' button for each product within the product set |  | Y | Y | Y | a | a | [10 empty] | No | Must Have | Design | Custom |  | Small |  | Launch | Launch |  | In
SF-092 | Search & Browse |  | PDP - Product Sets | PDP | As a business we want to remove the 'Add All To Bag' button on the product set PDP | - 'Add to bag' buttons are only surfaced under each product within the product set - There will be no option to add all products to the bag |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Design | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-093 | Search & Browse |  | PDP - Product Sets | PDP | As a business we want a clear line between the products within the product set on the PDP |  |  | Y | Y | Y | a | [11 empty] | Yes | Must Have | Design | OOTB |  | n/a |  | Launch | Launch |  | In
SF-094 | Search & Browse |  | PLP | Breadcrumbs | As a business we want navigation breadcrumbs to be surfaced on list pages and PDPs | - Applicable to both desktop and mobile |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-095 | Search & Browse |  | PLP | Colours | As a business we want to highlight that other colour variants exist for a product by surfacing the text "More Colours" on the PLP product tile | - PLP product tile surfaces the text "More Colours" if other colour variations exists - PLP product tile does not surface colour swatches - these are only surfaced on the PDP |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-096 | Search & Browse |  | PLP | Colours | As a business we want to show all colour variations of a product as individual products on a PLP | - Each colour variation of a product is surfaced as its own product on the PLP - The PLP product tile surfaces the text "More Colours" to highlight to a customer that other colour variations exist. This navigates to the PDP - Each colour variation is linked to the other colour variations through colour swatches on the PDP |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-097 | Search & Browse |  | PLP | Images | As a business we want list page images to swap on image hover over | - Hover over image on a list page will swap the image from front view to back view - Image swap will only surface on desktop |  | Y | Y | Y | a | [11 empty] | Yes | Must have |  | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-098 | Search & Browse |  | PLP | Product Badges | As a business we want product badges on the PLP product tiles to highlight to a customer where a product is on promotion | - PLP product tile surfaces a product badge if there is an applicable product-level promotion against the product - Product badge should be surfaced adjacent to the Was/Now pricing however the look & feel will be design dependent - Product badge design should be the same as the promotional icon that will be displayed on the PDP - Promotion details will not be surfaced on the badge or product tile (customer should navigate to the PDP to see the promotion details) |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Small | The business logic to determine if the promotional badge should display will be handled by the ecomm platform | Phase 2 | Out of Scope |  | Out
SF-098.1 | Search & Browse |  | PLP | Product Badges | As a business we want to display a dynamic badge icon on the PLP product tile to highlight to a customer where a product is "special" | - PLP product tile surfaces a product badge if the product is "New in" - PLP product tile surfaces a product badge if the product has limited stock left - PLP product tile surfaces a product badge if the product is an exclusive product | [17 empty] | Could Have / Wont Have |  | Custom |  | Small | The business logic to determine if the product badge should / should not be displayed, and the priority order of the badges (if only 1 should display) should be handled by the PIM. The information should be provided within the product catalog. Please refer to the Jones Bootmaker site to see examples of product badges (for "New In" items) | Phase 2 | Out of Scope |  | Out
SF-099 | Search & Browse |  | PLP | Quick View | As a business we want a product quick view that is surfaced on the PLP by selecting a quick view icon on the product tile | - Quick view lightbox is surfaced upon click/tap on the quick view icon - Quick view is not surfaced on image hover - Quick view icon is as per Avenue32 design |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | In
SF-100 | Search & Browse |  | PLP | Quick View | As a business we want to remove the Previous/Next scrolling icons from the quick view lightbox |  |  | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | TAS |  | n/a |  | Launch - TBC | Launch |  | In
SF-101 | Search & Browse |  | PLP | Refinements | As a business we want the mobile PLP refinement filters to surface at the top of the PLP | - Filters are surfaced at the top of the mobile PLP - The following filters are surfaced on mobile: Size, Colour - Filter options should be titled "Refine By" - Filter order should be configurable by a business user - Filter options should be displayed under the "Sort Results By" options - Filters should be animated on open/close (as per Saba mobile site) - Filters should utilise the native mobile drop-down filter functionality | Saba, Matches | Y | Y | Y |  | a | [10 empty] | Yes | Must Have |  | Custom |  | Small | Please refer to the Jones Bootmaker and/or Avenue32 mobiles site to see examples how the refinement filters could be surfaced | Launch | Out of Scope |  | In
SF-102 | Search & Browse |  | PLP | Refinements | As a business we want the mobile PLP sorting options to surface at the top of the PLP | - Sorting options are surfaced at the top of the mobile PLP - Sorting options should be titled "Sort Results By" - Sorting options order should be configurable by a business user - Sorting options should utilise the native mobile drop-down filter functionality - Sorting should be animated on open/close (as per Saba mobile site) - Sorting options should be displayed above the "Refine By" options - Sorting should be animated on open/close (as per Saba mobile site) - The sorting options that are surfaced on mobile are still TBA | Saba, Matches | Y | Y | Y |  | a | [10 empty] | No | Must Have |  | Custom |  | Small | Please refer to the Jones Bootmaker and/or Avenue32 mobiles site to see examples how the sorting filters could be surfaced | Launch | Out of Scope |  | In
SF-103 | Search & Browse |  | PLP | Refinements | As a business we want pagination on list pages |  |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-104 | Search & Browse |  | PLP | Refinements | As a business we want the sort option selection and pagination options to surface at both the top and bottom of a list page |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-105 | Search & Browse |  | PLP | Refinements | As a business we don’t want to offer a 'list view' option on the PLP | - List view option will not be surfaced on the PLP |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-106 | Search & Browse |  | PLP | Refinements | As a customer I want the ability to choose the number of products displayed on a list page | - A customer will have the option to view a max. of 96 items per page on desktop - There will be no 'View All Items' option - Max. no. of items per page on mobile will be design led |  | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | Out
SF-107 | Search & Browse |  | PLP | Refinements | As a customer I want to see what page no. I am viewing and how many pages there are in total on a paginated list page | - This be surfaced as " Page X of Y" - Placement of this will be design led - This will not be surfaced on mobile |  | Y | Y | Y | a | [11 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-108 | Search & Browse |  | PLP | PLP | As a business we want to surface 2 product tiles per row on the mobile PLP | - 2 product tiles per row are surfaced on the mobile PLP - Product tiles should surface the following data: Product Name, Was/Now price, Promotional Badge (if applicable), however promotional price is not surfaced - same as desktop product tiles |  | Y | Y | Y |  | a | [10 empty] | Yes | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-109 | Search & Browse |  | PLP | PLP | As a business we do not want to surface a list page banner on a mobile PLP | - List page banner is not surfaced on mobile PLP - The list page title (e.g. Bikini Tops) will be surfaced, however a banner image will not be surfaced |  | Y | Y | Y |  | a | [10 empty] | Yes | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-110 | Search & Browse |  | PLP | PLP | As a business we want to remove the 'Compare' checkbox from the product tile on a list page | - Compare checkbox is not surfaced |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-111 | Search & Browse |  | Search | Hidden Categories | As a business we want the ability to stop products within a hidden category from appearing within the search | - Products within hidden categories do not appear within the search results |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | n/a |  | n/a | This should be handled by the PIM when producing the product catalogs - the 'searchable' flag against the product should be set as non-searchable | Launch | Launch |  | in
SF-112 | Search & Browse |  | Search | Navigation | As a business we want a search icon to display within the mobile burger menu |  | ASOS | Y | Y | Y |  | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-113 | Basket & Checkout |  | Mini-bag | Mini-bag | As a business we want to remove the 'quantity' field from the mini-bag | - Unit quantity is not surfaced on mini-bag as PDP changes will only allow 1 unit to be added to the bag at a time - If multiple units of a SKU are added to the bag, these will be surfaced as separate items within the mini-bag |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | Out
SF-114 | Basket & Checkout |  | Mini-bag | Mini-bag | As a business we do not want the mini-bag to surface on the basket page | - selecting the mini-bag icon when on the basket page will not surface the mini-bag - selecting the mini-bag icon when on any of the checkout pages will not surface the mini-bag |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | Out
SF-115 | Basket & Checkout |  | Mini-bag | Mini-bag | As a business we want a 'Checkout' button on the mini-bag | - 'Checkout' button will replace the SiteGenesis 'View Cart' button - 'View Cart' will be a hyperlink and replace the SiteGenesis ''or go straight to checkout" text underneath the Checkout button - The Checkout button and View Basket hyperlink will be stacked above each other |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | In
SF-116 | Basket & Checkout |  | Mini-bag | Mini-bag | As a business we don’t want to surface the accordian open/close for the product image on the mini-bag | - Image accordion open/close is not surfaced next to product images on the mini-bag (for both desktop & mobile) - Product image is always visible and cannot be hidden |  | Y | Y | Y |  | a | [10 empty] | No | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | Out
SF-117 | Basket & Checkout |  | Mini-bag | Mini-bag | As a business we don’t want an accordion display surfaced for product images on the desktop mini-bag | - Image accordion open/close is not surfaced next to product images on the desktop mini-bag - Product image is always visible and cannot be hidden |  | Y | Y | Y | a | [11 empty] | No | Should Have |  | Custom |  | Small | DUPLICATE REQUIREMENT (SEE #SF-116 INSTEAD) | n/a | n/a |  | Out
SF-118 | Basket & Checkout | Yes | Basket | Abandoned Basket | As a business we want to be able to monitor and managed basket abandonment | - The ecomm platform will be integrated with a 3rd party basket abandonment tool via Google Tag Manager to manage basket abandonment |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | n/a |  | n/a | Seafolly to make a descision on the 3rd party by end June (either Salecycle/ or Yieldify) Integration will be via Google Tag Manager and will be managed by Seafolly - therefore this requirement requires no effort from Tryzens to implement If a different 3rd party is chosen and Tryzens effort is required, this will need to re-estimated. | Launch | Launch |  | In
SF-119 | Basket & Checkout |  | Basket | AfterPay | As a business we want to show AfterPay instalment payment information on the basket | - AfterPay information is only surfaced on AU sites - AfterPay messaging is surfaced near the order totals section (location is design dependent) - The messaging includes the number of instalments and payment due at each instalment |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope | On the AS-IS site, AfterPay is not surfaced on the mini-basg so proposing this culd be descoped until a later phase | In
SF-120 | Basket & Checkout |  | Basket | Basket | As a business we want the unit quantity on the basket to be an un-editable field | - PDP changes will only allow 1 unit to be added to the bag at a time - If multiple units of a SKU are added to the bag, these will be surfaced as separate items within the mini-bag and basket |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-121 | Basket & Checkout |  | Basket | Basket | As a business we want to remove the 'Update Cart' button from the basket page |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-122 | Basket & Checkout |  | Basket | Basket | As a business we don’t want to surface a "Continue Shopping" call to action on the basket page | - The basket page does not surface a "Continue Shopping" call to action |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-123 | Basket & Checkout |  | Basket | Payment Options | As a business we want a content spot on the basket page so that we can surface information to the customer regarding accepted payment types | - Content spot location will be design dependent - The content asset (e.g. logos of payment types) that is surfaced within this content spot will be managed by a business user through Business Manager |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-124 | Basket & Checkout |  | Basket | Recommendations | As a business we don’t want to surface product recommendations on the basket page | - Product recommendations are not surfaced on the basket page |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-125 | Basket & Checkout |  | Checkout | 1-page checkout | As a business we want to surface a single page checkout | - Single page checkout will be as per the Cotton:On customisations - Additional requirements are TBC, pending a business decision | Cotton:On | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Extra Large | This has been updated (from previous BRD submissions) as mobile designs have been provided by Seafolly. This estimate also includes the effort to deliver the following custom checkout page requirements: SF-128, 129, 130, 131, 133, 138, 139, 140, 141, 142, 145 and 147 As only mobile designs have been provided, the following assumptions have been made on this estimate: - Desktop functionality will be the same as mobile; however page designs may differ - On the mobile designs, where the functionality is not obvious from the design, we have assumed that the Cotton On user journey will implemented (e.g. customer log in and changing billing address) | Launch | Launch |  | In
SF-126 | Basket & Checkout | Yes | Checkout | Addresses | As a business we want address validation on shipping address and billing address entry pages in the checkout | - The ecomm platform will be integrated with PCA Predict - Address information will be validated as the customer enters the text |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | TAS | Postcode look-up tool integration | n/a | The implementation would be done on both My Account and Checkout pages | Launch | Launch |  | In
SF-127 | My Account |  | My Account Addresses | Addresses | As a business we want address validation on My Account address pages | - PCA Predict Address validation will apply to the Address entry fields within My Account |  | Y | Y | Y | [12 empty] | No | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-128 | Basket & Checkout |  | Checkout | Addresses | As a business we want to surface site-specific address fields for shipping & billing address entry on checkout pages | - Specific requirements are TBD - pending further info from business |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch - TBC | Launch | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-129 | Basket & Checkout |  | Checkout | Addresses | As a business we want to surface the "Country" field before any other address field on the shipping address page | - "Country" field is surfaced before other address fields - Other address fields are surfaced below Country field (Address 1, Address 2, City/Town, Postal Code) |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-130 | Basket & Checkout |  | Checkout | Addresses | As a business we want the data entered into the "Country" field to change the subsequent address fields and make them country-specific | '- Specific requirements are TBD - pending further info from business |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-131 | Basket & Checkout |  | Checkout | Addresses | As a business we want the phone number entry field to be a non-mandatory field when capturing shipping address | - Phone number field is non-mandatory on the shipping address page |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch | UPDATE | Out
SF-132 | Basket & Checkout |  | Checkout | Addresses | As a business we want validation on the phone number field on the shipping address page | - Field accepts both mobile and landline numbers - Phone number is validated to ensure it is inputted accurately |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small | REQUIREMENT NO LONGER VALID | n/a | n/a |  | Out
SF-133 | Basket & Checkout |  | Checkout | Addresses | As a business we want the default state for the checkbox (on the shipping address page) for "use same address for billing" to be ticked | - The default state for the checkbox for "use same address for billing" is ticked - A customer will untick the checkbox if they wish to enter a different billing address |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-134 | Basket & Checkout |  | Checkout | Addresses | As a business we want the checkout address fields to be pre-populated with the previously entered address details if a customer attempts to edit the address at later stage in the checkout process | - When editing a previously submitted address on the checkout pages, the address fields are pre-populated with the previously submitted information when returning to the page - The address fields are not blank/empty |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-135 | Basket & Checkout |  | Checkout | Addresses | As a business we do not want to offer the option to deliver to multiple addresses | - The 'Do you want to ship to multiple addresses?' message will not be surfaced - A customer will only be able to enter a single shipping address for the order |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-136 | Basket & Checkout |  | Checkout | Checkout | As a business we don’t want to display a customer services contact number on the checkout pages |  |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-137 | Basket & Checkout |  | Checkout | Checkout | As a business we want to remove the 'Is this a gift' message from the checkout pages |  |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-138 | Basket & Checkout |  | Checkout | Checkout | As a business we want to remove the order summary page within the checkout pages | - Order Summary page will not be surfaced - After payment details are successfully captured, the order confirmation page will be surfaced |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch | UPDATE | Out
SF-139 | Basket & Checkout |  | Checkout | Data | As a business we want the ecomm platform to restrict all customer-populated order fields to a maximum of 30 characters so that orders are not rejected by the WMS | - The following fields should be restricted to max 30 characters: shipping address fields, billing address fields, customer name fields, customer email field, message field(s) - Restrictions will not apply to payment fields as these will be hosted |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) Address validation will not be subjected to the 30 character cut off. Instead Salesforce will allow input of the full address from the address validation tool and truncate this to 30 characters (if required) before sending the order to the backend systems | Launch | Launch |  | In
SF-140 | Basket & Checkout |  | Checkout | Footer | As a business we want a checkout-specific footer to minimise drop-out within the checkout stages | - The checkout-specific footer will contain a single content spot - A business user will manage the content assets that display within this content spot within the Business Manager |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch |  | In
SF-141 | Basket & Checkout |  | Checkout | Header | As a business we want a checkout-specific header to minimise drop-out within the checkout stages | - Checkout-specific header will be design dependent - Brand logo will be surfaced - The search box is not surfaced |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch |  | In
SF-142 | Basket & Checkout |  | Checkout | Landing Page | As a business we want the Checkout landing page to display 'Returning Customer' and 'Guest or New Customer' checkout options | - On desktop 'Returning Customers' should be on the left of the page; 'Guest or New Customers'; should be on the right (as per the layout on the My Account landing page) - On mobile 'Returning Customers' should be above 'Guest or New Customers' |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch | Launch | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-143 | Basket & Checkout |  | Checkout | Landing Page | As a business we don’t want to offer social log-in as an option on the checkout landing page | - Social log-in functionality should be disabled |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Phase 2 | Launch | UPDATE | Out
SF-144 | Basket & Checkout |  | Checkout | My Account | As a business we want to surface a content spot on the order confirmation page so that we can inform customers of the benefits of creating an account | - Content spot location will be design dependent - The content asset (e.g. account benefits text) that should be surfaced within this content spot will be managed by a business user through Business Manager |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small |  | Launch | Out of Scope | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | Out
SF-145 | Basket & Checkout |  | Checkout | Order Summary | As a business we don’t want the mini-order summary (where product data is displayed) to be editable within the checkout pages | - The mini Order Summary box within checkout pages is not editable - The "edit" hyperlink is not surfaced |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch - TBC | Launch | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-146 | Basket & Checkout |  | Checkout | Order Summary | As a business we want to hide the quantity field on the mini-order summary within the checkout pages | - Quantity field is not surfaced by each product within the mini Order Summary on the checkout pages |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-147 | Basket & Checkout |  | Checkout | Order Summary | As a business we want to hide the product on the mini-order summary within the checkout pages | - Product image is not surfaced on the mobile mini-order summary on the checkout pages - Only product details (name, SKU number, colour, size, unit price) are surfaced on the mobile mini-order summary |  | Y | Y | Y |  | a | [10 empty] | No | Should Have |  | Custom |  | Small | The effort estimate for this is included within SF-125 (one-page checkout) | Launch - TBC | Launch | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-148 | Basket & Checkout |  | Checkout | Promotions | As a business we want to remove the promo code/coupon entry field on the checkout to minimise drop-out within the checkout stages | - Promo code/coupon entry field is not surfaced on the billing address page |  | Y | Y | Y | a | a | [11 empty] | Should Have |  | Custom |  | Small | This is estimate is based on the OOTB multi-page checkout flow. Seafolly to make a descision on single page checkout (by June 12th). This requirement may need to be re-estimated once a decision is made | Launch - TBC | Out of Scope | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | In
SF-149 | Basket & Checkout |  | Checkout | Shipping | As a business we want to offer a 'click & collect' delivery service to customers | - Specific requirements are TBD - pending business decision on a 3rd party fulfilment provider (e.g. PureComm) |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Small | The effort estimate provided is based on delivering the Click & Collect workflow as per the Whistles site customisation. However, if a more complex solution is required (i.e. similar to the Jones Bootmaker site MetaPack integration) then the effort estimate increases to Extra Large | Phase 2 | Out of Scope |  | Out
SF-150 | Basket & Checkout |  | Checkout | Shipping | As a business we want to offer international shipping to our customers | - Specific requirements are TBD - potentially provide through BorderFree or Global-e (pending business decision) |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Large | This estimate is based on the assumption that a 3rd party tool with a cartridge is implemented. | Phase 2 | Out of Scope |  | Out
SF-151 | Basket & Checkout |  | Checkout | Shipping | As a business we want the shipping method selection on the checkout page to be a drop down selection filter | - This should utilise the native drop down filter functionality within desktop, tablet & mobile |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | Out
SF-152 | Basket & Checkout |  | Checkout | Subscriptions | As a business we want a privacy policy hyperlink to appear at the end of the marketing opt in message | - The privacy policy hyperlink will navigate to a static page |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small |  | Launch | Launch |  | In
SF-153 | Basket & Checkout |  | Checkout | Subscriptions | As a business we want to add a marketing opt-in on the order confirmation page for guest checkout customers |  |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small |  | Launch | Launch |  | In
SF-154 | Basket & Checkout | Yes | Payment | AfterPay | As a business we want to offer the customer the option to pay for their order in instalments | - The ecomm platform will be integrated with AfterPay - The checkout will surface AfterPay as a payment option - The AfterPay integration will be hosted (i.e. the customer will be directed off-site to the AfterPay payment page/portal) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom | AfterPay integration | Medium | The estimate here is based on re-using some the Cotton:On logic | Launch | Launch |  | In
SF-155 | Basket & Checkout | Yes | Payment | AP21 Gift Vouchers | As a business we want to allow a customer to purchase an AP21-generated gift voucher | - A customer can purchase an AP21-generated gift voucher through the ecomm platform - Gift vouchers can be bought for pre-determined amounts - these amounts are $50, $100, $150, $200, $300 and $500 - The ecomm platform surface the following fields when a customer opts to buy a gift voucher: Recipient's email, Email subject, Personal Message, Sender name, Receiver name - The ecomm platform will send an email to the receiver providing the gift voucher serial number and PIN number for redemption - Gift voucher purchases can be paid for using all payment methods (including AfterPay) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Large | The specific data flows need to be confirmed with Fusion Factory / AP21 | Launch | Launch |  | In
SF-156 | Basket & Checkout | Yes | Payment | AP21 Gift Vouchers | As a business we want to offer a customer the option to check the balance of their AP21-generated gift voucher | - A customer can check the balance of their Gift Voucher online |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Medium | The specific data flows need to be confirmed with Fusion Factory / AP21 | Phase 2 | Out of Scope |  | Out
SF-157 | Basket & Checkout | Yes | Payment | AP21 Gift Vouchers | As a business we want to offer a customer the option to redeem an AP21-generated gift voucher | - A "pay with gift voucher" checkbox will be surfaced within the 'select payment method section on the checkout - When the checkbox is ticked by the customer, a gift voucher serial number field and a gift voucher PIN number field will be surfaced - If a customer unticks the checkbox, these 2 fields are hidden - A customer will enter both the gift voucher serial number and PIN number to redeem the voucher - A customer can split payment across an AP21-generated gift voucher and a single payment card online if the gift voucher amount is less than the order value - The ecomm platform will adhere to AP21- generated gift voucher expiry dates and not accept the gift voucher as payment if the expiry has passed - The gift voucher can only be used on the site it was issued (i.e. same currency for purchase and redeeming) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must have |  | Custom |  | Large | The specific data flows need to be confirmed with Fusion Factory / AP21 | Launch | Launch |  | In
SF-158 | Basket & Checkout | Yes | Payment | AP21 Gift Vouchers | As a business we want to be able to refund to an AP21-generated gift voucher | - When a full or partial order refund is due: = If split payment has occurred, the ecomm platform will prioritise the credit card refund and request a refund from the PSP. = If the refund amount is greater than the credit card amount and there is a balance to refund, then the ecomm platform will send a notification to AP21 to reissue the gift voucher = once the gift voucher has been re-issued, the ecomm platform will receive a notification via the middleware and the ecomm platform will trigger an email to the customer to advise that the gift voucher has been refunded |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Medium | The specific data flows* need to be confirmed with Fusion Factory / AP21 and the chosen PSP The refund for process for AfterPay and PayPal/PayPal express in currently unidentified and this could increase the effort estimate The business logic re: how a gift voucher is re-issued must be managed by AP21/Fusion Factory *An OSU feed implementation is also required to deliver this requirement - effort estimate for this feed is under SF-182 | Launch | Launch |  | In
SF-159 | Basket & Checkout | Yes | Payment | Gift Cards | As a business we want an omni-channel, multi-currency, multi-brand gift card solution across the whole business | - Specific requirements are TBD - pending business decision on a 3rd party gift card provider |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom | 3rd party gift card provider integration | Extra Large | This estimate is based on the assumption that a 3rd party tool with a cartridge is implemented. | Phase 2 | Out of Scope |  | Out
SF-160 | Basket & Checkout |  | Payment | Payment Options | As a business we don’t want to offer a 'bill me later' payment option to customers |  |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-161 | Basket & Checkout |  | Payment | Payment Options | As a business we want a content spot on the checkout payment page so that we can surface information to the customer regarding accepted payment types | - Content spot location will be design dependent - The content asset (e.g. logos of payment types) that is surfaced within this content spot will be managed by a business user through Business Manager | Cotton:On | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope | Checkout page requirements may change based on one-page checkout; therefore proposing to descope these from launch and review in line with a one-page checkout implemenatation | Out
SF-162 | Basket & Checkout | Yes | Payment | PayPal | As a business we want to offer PayPal as a payment method | - PayPal will be implemented via the PSP (BrainTree) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | TAS |  | n/a | This has been updated (from previous BRD submissions) and is now marked as TAS This is becasue PayPal will be implemented via the chosen PSP (BrainTree) and is part of the cartridge. Therefore there is no customisation effort required to deliver this requirement | Launch | Launch |  | in
SF-163 | Basket & Checkout | Yes | Payment | PayPal Express | As a business we want to offer PayPal Express as a payment method from the mini-bag and/or basket page | - PayPal express will be a payment option from the mini-bag - PayPal express will be a payment option from the basket |  | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | Custom | PayPal integration | Small | This has been updated (from previous BRD submissions) and is now marked as small effort This is because the cartridge for the chosen PSP (BrainTree) provides an intgration for PayPal express, however some additional customisation is required to deliver this requirement in full | Launch - TBC | Launch |  | In
SF-164 | Basket & Checkout | Yes | Payment | PSP Hosted Payment | As business we want the payment part of the checkout process to be a hosted solution so that we don’t have an additional PCI compliance overhead | - The chosen PSP has been confirmed as BrainTree (and a LINK cartridge exists for this) - PayPal will be implemented as part of the PSP |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-165 | Basket & Checkout |  | Payment | Reconciliation | As a business we want access to payment reconciliation reporting |  |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | n/a |  | n/a | This could be provided by either the PSP or middleware solution and requires further business investigation / decision & requirements | Launch | Launch |  | In
SF-166 | Basket & Checkout |  | Payment | Returns & Refunds | As a business we want to offer a credit note for returns to encourage the customer to re-purchase from Seafolly | - Credit notes will be implemented through Gift Voucher/Card functionality - Credit note value should be configurable i.e. the business can choose to offer 100% of the return value or greater (e.g. 110% of the return value) - The credit note can be configurable against specific return reasons e.g. only eligible against returns due to fit issues - The credit note will only be redeemable online (i.e. it will not be a multi- or omni-channel credit note) |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Medium |  | Phase 2 | Out of Scope |  | Out
SF-167 | Basket & Checkout |  | Payment | Returns & Refunds | As a business we want the ecomm platform to manage both the payment capture and refund process | - The ecomm platform will trigger a refund after receiving the returned order status update from middleware - Specific requirements are TBC pending a business decision on the PSP |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Small | An OSU feed implementation is also required to deliver this requirement - effort estimate for this feed is under SF-182 | Launch | Launch |  | In
SF-168 | Basket & Checkout |  | Payment | Returns & Refunds | As a business we want an RMA process online so that we can manage the returns process more easily | - A registered & logged in customer can request an RMA through the My Account>Order History section of the website (RMA process will not be available on guest checkout orders) - A customer can request to return a single item within an order or return the whole order - The ecomm platform will capture mandatory data regarding the return i.e. the reason for return (by line item). This data is TBA. - Тhe ecomm platform will surface an RMA number to the customer upon successful completion of the RMA process - The ecomm platform will send the RMA number to Seafolly's back -end systems to allow the warehouse to have visibility to the return request - Once Seafolly's back-end systems have completed the return workflow, the middleware will notify the ecomm platform to initiate the refund process '- Once the refund is complete, the ecomm platform will trigger an email to the customer to advise that the gift voucher has been refunded. The email content and look & feel should be customisable | The Iconic, Avenue32 | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Large | The business logic for generating an RMA number are still to be determined The specific data flows* and notification formats need to be confirmed with Fusion Factory / AP21 The refund process will need to be initiated by the WMS - the RMA number from the ecomm platform will not trigger any systemic return/refund workflow *An OSU feed implementation is also required to deliver this requirement - effort estimate for this feed is under SF-182 | Phase 2 | Out of Scope |  | Out
SF-169 | Basket & Checkout | Yes | Payment | Sales Tax | As a business we want accurate sales tax calculated at checkout | - The ecomm platform will be integrated with a 3rd party sales tax tool to calculate sales tax after shipping address has been captured - Sales tax will be calculated on the Seafolly US site only |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | TAS |  | n/a | This estimate is based on the assumption that a 3rd party tool with a cartridge is implemented (e.g. Avalara , Duty Calculator etc.) If a 3rd party without a cartridge is chosen, the this would be a medium level of effort to implement | Launch | Launch |  | In
SF-170 | My Account |  | My Account | Landing Page | As a business we want the My Account landing page on the mobile site to display Registered Customer log-in and New Customer create account only | - Social log-in functionality should be disabled - 'Check Order' functionality should be removed |  | Y | Y | Y |  | a | [10 empty] | Yes | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-171 | My Account |  | My Account | My Account | As a customer I want the My Account header icon to visibly change once I log in so that it's clear that I'm logged in to my account |  | The Iconic | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | Out
SF-172 | My Account |  | My Account | Order History | As a business we want the 'Check Order' functionality to be a link in the footer rather than displayed on the My Account landing page | - 'Check Order' is surfaced as a link in the footer (and it is not surfaced in the checkout specific footer) - For a signed in customer, selecting this link will navigate them to the My Account pages for them to check order status - For a non-signed in customer, selecting this link will navigate them to a static page where they will be prompted to enter the following details for them to check order status: Order number, Order email, Billing postal code |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-173 | My Account |  | My Account | Payment Options | As a business we want to remove the 'Payment Cards' option from the My Account dashboard and left-hand navigation to avoid additional PCI compliance overheads | - Payment cards will not be a visible option to the customer |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-174 | My Account |  | My Account | Preferences | As a business we want to capture the customer's country of residence at account sign-up so that we can target them with seasonal-appropriate marketing |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-175 | My Account |  | My Account | Preferences | As a business we want to capture a customer's DOB and (mobile) phone number within My Account personal data | - DOB and phone number will not be surfaced as part of account creation - These will be non-mandatory fields - These fields will be surfaced under a 'preferences' section |  | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | Out
SF-176 | My Account |  | My Account | Preferences | As a business we want to capture a customer's marketing preferences within My Account | - e.g. Brands or product area of interest |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Small |  | Phase 2 | Out of Scope |  | Out
SF-177 | My Account |  | Order History | Order History | As a business we want the ecomm platform to show the updated order statuses within the My Account Order History area so that a customer has visibility to it | - A customer can see the following order statuses within the order details screen: Order Confirmed, Order Shipped (with tracking information), Order Refunded |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | An OSU feed implementation is also required to deliver this requirement - effort estimate for this feed is under SF-182 | Launch | Out of Scope |  | Out
SF-178 | My Account |  | Order History | Order History | As a business we want the ecomm platform to surface a customer's omni-channel order history | - For registered and signed in customers only - My Account will display both online and store order history |  | Y | Y | Y | a | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Medium |  | Phase 2 | Out of Scope |  | Out
SF-179 | My Account |  | Wish List | Wish List | As a business we want to rename ' Find Someone's Wish List' within My Account>Wish list to be called ' Find A Wish List' instead | - Customer sees 'Find A Wish List' on the My Account Wish list page - Customer sees ' Find A Wish List' on the My Account landing page when accessing wish list from the footer |  | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | TAS |  | n/a |  | Launch - TBC | Launch |  | In
SF-180 | My Account |  | My Account | Gift Registry | As a business we want to remove the 'Gift Registry' option from the My Account dashboard and left-hand navigation | - Gift Registry will not be a visible option to the customer |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | TAS |  | n/a |  | Launch | Launch |  | In
SF-181 | Emails |  | Service Emails | Service Emails | As a business we want service emails to be sent to the customer from the ecomm platform | - The platform will send the following service emails: = Forgot Password = New Order (Order Confirmation) = Share Wish list |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-182 | Emails | Yes | Service Emails | Service Emails | As a business we want additional service emails to be sent to the customer from the ecomm platform | - The platform will send the following service emails. Emails are triggered based on order status updates from AP21 via PIM/middleware: = New Account Creation = New Shipment (Order Shipped) contains the courier tracking number and website URL = Order Cancelled = Refund = Gift Voucher (AP21 voucher) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have | Legacy | TAS |  | n/a | An 'Order Status Update' (OSU) feed* needs to be implemented to achieve this reqiurement. The effort for implementing the OSU feed is included as part of the TAS package *This OSU feed implementation is also required to partially deliver the following requirements: SF-158, SF-167, SF-168, SF-177, SF-189. However additional effort is required to deliver these requirements in full | Launch | Launch |  | In
SF-183 | Emails |  | Service Emails | Email Management | As a business we want to be able to configure the content, look & feel of all service emails | - Email content & look & feel should be customisable by a business user using an email template - There are 8 email templates identified: Forgot Password, New Order (Order Confirmation), Share Wish List, New Account Created, New Shipment (Order Despatched), Order Cancelled, Order Refunded, Gift Voucher Purchase |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Medium | This estimate covers the 5 customised emails in SF-182 (not the OOTB emails in SF-181 - the effort for these is included within the TAS package). An assumption has been made that all the order-related emails (order Shipped, Order Cancelled, Order Returned/Refunded) will be identical with only the messaging being different, hence the reduced estimate from previous BRD submissions. If this is not the case, the effort will remain LARGE A single email template (covering both desktop & mobile) would need to be created for each required custom email (approx. 3 days effort per template). Tryzens recommend a maximum template width of 600px to ensure that each email is able to be displayed properly on desktop (full resolution) and mobile (with side scrolling) Tryzens also recommend that the email module is implemented when creating these tempalates. It is part of the TAS OOTB solution and would enable Seafolly (through a front-end developer) to make changes to the email templates provided without additional effort from Tryzens. | Launch | Launch |  | Out
SF-184 | Emails |  | Service Emails | Email Management | As a business we want to be able to re-send service emails to customer | - All order-related service mails can be re-sent to a customer by a business user if required (Order Shipped, Order Cancelled, Order Refunded) |  | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | Custom |  | Small | This would require implementation of the Tryzens Email Module - emails can be re-sent from the relevant storefront (site). This estimate is for the 3 custom order-related emails only (Order Shipped, Order Cancelled, Order Returned/Refunded) | Launch - TBC | Out of Scope |  | Out
SF-184.1 | Emails |  | Service Emails | Email Management | As a business we want to be able to re-send service emails to customer | - All order-related service mails can be re-sent to a customer by a business user if required (Order Confirmation) |  | Y | Y | Y | a | a | [10 empty] | Yes | Should Have |  | TAS |  | n/a | This would require implementation of the Tryzens Email Module - emails can be re-sent from the relevant storefront (site). | Launch - TBC | Launch |  | In
SF-185 | Emails |  | Service Emails | Email Management | As a business we want to be able to switch service emails on/off for each of the order status updates |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope |  | Out
SF-186 | Emails | Yes | Subscriptions | Subscriptions | As a business we want an newsletter sign up that integrates with our marketing ESP | - A customer can subscribe to the newsletter via the footer (but not on the checkout-specific footer) - A customer can subscribe to the newsletter via My Account/Register and My Account/Edit - A customer can subscribe to the newsletter via the Billing Address entry page on the checkout - A customer can subscribe to the newsletter via the Order Confirmation page (if they have used Guest Checkout) - Customers will need to enter the following mandatory fields to subscribe: Name, Email, DOB - There will be a subscription data export to the middleware; the middleware will send the data to the ESP (Campaign Monitor) |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Medium | This is a high level estimate only and it would need to be re-reviewed once Tryzens have received the integration document(s) from Campaign Monitor. | Launch | Launch |  | In
SF-187 | Customer Services |  | Customer Services | Customer | As a business we want the ability to export customer data from the ecomm platform | - A business user can extract customer data from the ecomm platform - Data will be extracted from Business Manager into an excel spreadsheet |  | Y | Y | Y | a | a | [10 empty] | ? | Must Have |  | Custom |  | Medium |  | Launch | Out of Scope |  | Out
SF-188 | Customer Services |  | Customer Services | Customer | As a business we want to surface a customer engagement tool on the ecomm platform | - As customer will be able to access a Live Chat function on the ecomm platform |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | n/a | INSIDE integration | n/a | Seafolly have confirmed that they will use a 3rd party tool called Insight, which will be integrated with the ecomm platform through Google Tag Manager. No direct platform integration has been identified. | Launch | Launch |  | In
SF-189 | Customer Services |  | Order History | Order History | As a business we want the ecomm platform to show the updated order statuses within the Customer Services tool so that a Customer Services representative has visibility to it | - A customer services representative can see the following order statuses within the order details screen in the Customer Services tool: Order Confirmed, Order Shipped (with tracking information), Order Refunded |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Small | An OSU feed implementation is also required to deliver this requirement - effort estimate for this feed is under SF-182 | Launch | Out of Scope |  | In
SF-190 | Data Migration |  | Customer | Customer | As a business we want to migrate approx. 89K online customers from Magento to the new platform | - Only online customer data will be migrated (approx. 51k of store-only customer data will not be migrated to the new platform) - The following customer data should be migrated: Name, Email, Subscription opt in/out status, ?? - Password data will not be migrated |  | Y | Y |  | a | a | [11 empty] | Must Have |  | Custom |  | Small | This estimate is based on the assumption that the data to be migrated will not be provided in Salesforce format, and therefore will require data mapping and conversion effort by Tryzens. If the data can be provided in Salesforce formats then the effort estimate will decrease Seafolly to confirm with Fusion Factory what effort would be required to create customer data files in Salesforce formats; until confirmation is received, Tryzens to provide initial plans and costs based on the requirement as-is Requirement re-estimated on the assumption that Fusion Factory will manage the data mapping and conversion activities | Launch | Launch |  | In
SF-191 | Data Migration |  | Customer | Customer | As a business we want migrated customers to be prompted to re-set their password upon first log-in on the new ecomm platform | - A migrated customer will be presented with a re-set password message when attempting to log into their existing account for the first time |  | Y | Y | [14 empty] | Must Have |  | Custom |  | Medium |  | Launch | Launch |  | In
SF-192 | Data Migration |  | Order History | Order History | As a business we want 2 years worth of Magento order history to be migrated to the new platform | - Order history will be at the order details level (i.e. product variations ordered, order costs, billing/shipping information) - Order history will contain the product variation images - Historical product and images for order history will be provided by the PIM in the master catalogue - Product details/images will not navigate to a PDP - The new platform will send service emails to customers for any of the migrated orders (if required by an order status update) |  | Y | Y |  | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Small | This estimate is based on the assumption that the data to be migrated will not be provided in Salesforce format, and therefore will require data mapping and conversion effort by Tryzens. If the data can be provided in Salesforce formats then the effort estimate will decrease Seafolly to confirm with Fusion Factory what effort would be required to create order data files in Salesforce formats; until confirmation is received, Tryzens to provide initial plans and costs based on the requirement as-is Requirement re-estimated on the assumption that Fusion Factory will manage the data mapping and conversion activities | Launch | Launch |  | In
SF-193 | SEO |  | 404 pages | 404 pages | As a business we want error pages to send a proper 404 https status code |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Launch |  | In
SF-194 | SEO |  | 404 pages | 404 pages | As a business we want a content slot on the 404 page so that we can inform customers that the requested content no longer exists |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-195 | SEO |  | Product Termination | Product Termination | As a business we want a permenant (301) re-direct for a terminated product to a similar category PLP where a content spot is surfaced to advise the customer of the redirect | - A business user will manage the mapping for the re-direct (i.e. detemine the new cateogry list page URL) - Once the customer has been re-directed to the new PLP, a content spot will be surface on the page to advise them of the re-direct - Example messaging for the content spot is: "sorry the product is no longer available, but we suggest the following collection" (actaul wording TBC/to be re-worked) | Adidas | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | This estimate is based on terminated products still being included in the product catalogs (PIM should exculde the terminate products from all categories so they do not appear in the navigation). This way, Seafolly can set up the redirects at product level. | Launch | Out of Scope |  | Out
SF-196 | SEO |  | Rich Snippets | Breadcrumb snippets | As a business we want breadcrumb snippets | - Page HTML code will include all relevant information - Page HTML code is structured following the same organisation than the website - Google should be able to read the breadcrumb code |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-197 | SEO |  | Rich Snippets | Open Graph integration | As a business we want an integration with Open Graph Facebook |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope | Can Seafolly provide some GA stats on how much social sharing occurs on the AS-IS site? If it's minimal, propose that this is descoped | In
SF-198 | SEO |  | Rich Snippets | Open Graph integration | As a business we want an integration with Open Graph Twitter |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small |  | Launch | Out of Scope | Can Seafolly provide some GA stats on how much social sharing occurs on the AS-IS site? If it's minimal, propose that this is descoped | In
SF-199 | SEO |  | Rich Snippets | Product Snippets | As a business we want product snippets | '- The following should be implemented: - name: the name of the product - brand : the brand of the product - image : the URL of a product photo. Pictures clearly showing the product - price : the price of the product. Follow schema.org usage guidelines. - priceCurrency : the currency used to describe the product price, in three-letter ISO 4217 format. - availability : value is taken from a constrained list of options, expressed in markup using URL links - reviews |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small |  | Launch | Launch |  | In
SF-200 | SEO |  | Robots | Robots | As a business we want a single robot.txt for all sub-directories on the EU site, however each sub-directory should have its own sitemap | - Requirement is still TBC, pending further info from Seafolly's SEO agency | Nike | Y | Y | Y | a | a | [10 empty] | No | Should Have |  | Custom |  | Small |  | Launch - TBC | Out of Scope |  | Out
SF-201 | SEO |  | SEO | Image alt text | As a business we want alternative text for images to follow a specific naming convention | - Alt text for images must adhere to this specific naming convention: [Seafolly] [Category] [Sub-Category] [Product Name] |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small |  | Launch | Launch |  | in
SF-202 | SEO |  | Site Speed | Load speeds | As a business we want pages to be downloaded in <2.5 seconds | Requirements TBD - awaiting specific requirements from Seafolly's SEO agency |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | n/a |  | n/a | This should be managed by the Seafolly team - careful management of rich content and images on pages is required to ensure page load speeds are not impacted. | Launch | Launch |  | In
SF-203 | SEO |  | Site Structure | Site Structure | As a business we want a pop-up that allows a customer to choose which site they want to view when landing on any Seafolly domain, instead of using automatic geo-location based on IP | - The seafolly.com URL will be re-directed to seafolly.com/au - A site-selector pop up will be surfaced when landing on seafolly.com/au only if geo-location detects that the customer's IP location is not in either AU or NZ = Cookies should be in place so that customers are only served the pop up when they arrive on seafolly.com/au for the first time; a non-AU/NZ based customer, who has visited the site before, will browse the .com/au site. If they want to switch to another site, they can select the required country from the country selector in the header. - The pop-up will have a site selector drop-down to allow the customer to select a site (Seafolly AU, Seafolly US or Seafolly SG) - The pop-up will also surface a message outlining which countries Seafolly can ship to - Geo-location will detect the customer's IP location and suggest an appropriate site by pre-selecting a site in the drop-down; however, automatic geo-location re-direction based on IP will not occur as the customer must confirm the site selection before being re-directed to the new site - A site-selector pop-up will not be surfaced if a customer opens the URL for the .com/us or .com/sg sites directly; instead, browsing settings would default to that site until the customer choses a different site via the site-selector in the header |  | Y |  |  | a | a | [10 empty] | No | Must Have |  | Custom |  | Medium |  | Launch | Out of Scope | As there will be a site selector in the header, prospose that this is descoped to the next phase of work | In
SF-204 | SEO |  | Site Structure | Site Structure | As a business we want AMP for category and landing pages for optimised SEO listing | Requirements TBD - awaiting (Google mobile first) requirements from Seafolly's SEO agency |  | Y | Y | Y |  | a | [10 empty] | No | Could Have / Wont Have |  | Custom |  | Small | Cannot define the exact effort without the final requirements. | Phase 2 | Out of Scope |  | Out
SF-205 | SEO |  | Site Structure | Site Structure | As a business we want H1 page structures to be configured correctly for optimised SEO | Requirements TBD - awaiting specific configuration requirements from Seafolly's SEO agency |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Small | Specific requirements wont be known until page designs are signed off (in Augusts - TBC); therefore the effort may need to be re-estimated | Launch | Launch |  | In
SF-206 | SEO |  | Site Structure | Site Structure | As a business we need the Href lang tags within the site maps to work within a multi-site environment | Requirements TBD - awaiting specific implementation / configuration requirements from Seafolly's SEO agency |  | Y | Y | Y | a | a | [10 empty] | Yes | Must Have |  | Custom |  | Small | High level estimate only, will need to be re-reviewed once details are provided by the SEO agency. Requirements are pending the results of a keyword study by Seafolly - this is due early July | Launch | Launch |  | In
SF-207 | SEO |  | Site Structure | Site Structure | As a business we want site structure to be optimised (pre-approved) for multi-currency trading | - All sites (across Seafolly, Sunburn & Milea) should be optimised for multi-currency trading at launch - Sites should not require additional platform development after launch to support multi-currency - this requirement will also be applicable to back-end systems (and will be managed by Seafolly business) |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | OOTB |  | n/a |  | Launch | Launch |  | In
SF-208 | SEO |  | Sitemaps | Sitemaps | As a business we want 3 separate sub-sitemaps for content, videos and images |  |  | Y | Y | Y | a | a | [11 empty] | Could Have / Wont Have |  | OOTB |  | n/a |  | Phase 2 | Out of Scope |  | Out
SF-209 | Tagging | Yes | Tagging | Google AdWord | As a business we want to implement Google AdWord tracking | Requirements TBD - awaiting specific requirements from Seafolly's SEO agency |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | Custom |  | Small | High level estimate only, will need to be re-reviewed once details are provided by the SEO agency | Launch | Out of Scope |  | In
SF-210 | Tagging | Yes | Tagging | GTM | As a business we want an implementation with Google Tag Manager (GTM) | Requirements for the data layer are TBC - awaiting specific requirements and information on AS-IS integration from Seafolly (Nathan/IT) and/or NetData |  | Y | Y | Y | a | a | [11 empty] | Must Have |  | Custom |  | Medium | High level estimate only, will need to be re-reviewed once data layer requirements have been reviewed | Launch | Launch |  | In
SF-211 | Reporting |  | Reporting | Reporting | As a business we want to implement the TradeState module to provide enhanced reporting & analytics capabilities |  |  | Y | Y | Y | a | a | [10 empty] | No | Must Have |  | TAS |  | n/a | It would be part of the Managed Service contract that Tryzens offer. | Launch | Launch |  | In
Note on Y2: Requirements Prioritisation: MoSCoW ratings M Must Have S Should Have C Could Have W Wont Have
Note on AA2: Minal Raeburn: OOTB (Out Of The Box) - provided as part of the standard Salesforce platform (SiteGenesis) TAS (Tryzens Accelerated Service) - the basic Salesforce platform with recommended 3rd party integrations (via cartridges) and specific storefront customisations Custom - Requires custom development to deliver and cannot be provided either OOTB or as part of TAS n/a - the requirement is not for Salesforce/Tryzens to implement. This may be a back-end requirement for another supplier
Note on X23: Minal Raeburn: Managed directly in Magento
Note on X36: Minal Raeburn: On AS-IS site, My Account is only surfaced in the burger menu and not in the header
Note on X45: Minal Raeburn: Through Four60 integration on Magento
Note on X46: Minal Raeburn: Through Four60 integration on Magento
Note on X47: Minal Raeburn: Through Four60 integration on Magento
Note on X48: Minal Raeburn: Through Four60 integration on Magento
Note on X49: Minal Raeburn: Through Four60 integration on Magento
Note on X50: Minal Raeburn: Through Four60 integration on Magento
Note on X59: Minal Raeburn: On Sunburn
Note on X64: Minal Raeburn: Scrolling is only possible on the zoom image; it's not available on the PDP image(s)
Note on H65: Minal Raeburn: O'Neill example: http://www.oneill.com/gb/en/shop/women/collections/mix-and-match-your-own-bikini#tt=active&tv=7A8546-4900&bt=shorty&bv=7A8573-4956
Note on X85: Minal Raeburn: AS-IS shows the number of units left per size. However when a size is OOS the size disappears from the filter
Note on X91: Minal Raeburn: Google+ is a social sharing option on the AS-IS site
Note on X92: Minal Raeburn: AS-IS site states "Love it? Share it!" next to the social sharing icons
Note on X96: Minal Raeburn: AS-IS surfaces a message "this is a required field" under each unselected variant
Note on X97: Minal Raeburn: There is no previous/next scrolling on the AS-IS site so marking this as Yes
Note on X103: Minal Raeburn: On AS-IS desktop site only. There are no breadcrumbs on the mobile site
Note on X113: Minal Raeburn: On desktop AS-IS site only. Mobile PLP has a 'load more' option
Note on X116: Minal Raeburn: AS-IS site options are view 48, 96 or all options
Note on X117: Minal Raeburn: AS-IS site options are view 48, 96 or all options
Note on X124: Minal Raeburn: On the AS-IS site there is no Basket Page - only a mini-basket that navigates to the checkout
Note on X126: Minal Raeburn: On the AS-IS mobile site there is no mini-bag or basket page - the mini bag icon in the header navigates to the checkout
Note on X129: Minal Raeburn: On the AS-IS site there is no Basket Page - only a mini-basket that navigates to the checkout
Note on X130: Minal Raeburn: On the AS-IS site there is no Basket Page - only a mini-basket that navigates to the checkout
Note on X131: Minal Raeburn: On the AS-IS site there is no Basket Page - only a mini-basket that navigates to the checkout
Note on X132: Minal Raeburn: On the AS-IS site there is no Basket Page - only a mini-basket that navigates to the checkout
Note on X133: Minal Raeburn: On the AS-IS site there is no Basket Page - only a mini-basket that navigates to the checkout
Note on X134: Minal Raeburn: On the AS-IS site there is no Basket Page - only a mini-basket that navigates to the checkout
Note on X143: Minal Raeburn: The AS-IS site has a 1-page checkout
Note on X144: Minal Raeburn: The AS-IS site has a 1-page checkout
Note on X145: Minal Raeburn: On the AS-IS site, a customer can only enter a single shipping address for an order
Note on X157: Minal Raeburn: On the AS-IS mobile site there is no mini-bag or basket page - the mini bag icon in the header navigates to the checkout
Note on X181: Minal Raeburn: 'Log In' wording in header changes to 'Account' once logged in
Note on X183: Minal Raeburn: Saving payment cards is not an option on the AS-IS site so this option is not present (hence marked as 'Yes')
Note on X190: Minal Raeburn: Gift Registry s is not an option on the AS-IS site so this option is not present (hence marked as 'Yes')

## MoSCoW Guidelines
Business requirements prioritisation using the MoSCoW technique
MoSCoW | Priority | Priority Meaning | Further Details / Explanation
M | Must Have | The requirement is critical in order for the project to deliver on its target date | Without this requirement, the project / implementation: - cannot be delivered at all - would not legal - would be unsafe - would not deliver the projected business case benefits
S | Should Have | The requirement is important, but not critical in order for the project to deliver on its target date | Without this requirement, the project / implementation: - would still be viable however there would be pain points for the business / end users to deal with - would require some workarounds to be put in place resulting in some inefficiencies, manual process etc.
C | Could Have | The requirement is desirable, but not important in order for the project to deliver on its target date | If left out, this requirement has less impact (compared with a "Should Have" requirement). However if project time, cost and resources permit, this requirement could: - help to improve user experience - help to improve customer satisfaction - help to improve business decision making
W | Wont Have | The requirement is the least critical, important or desirable as it is the lowest-payback item, and is not appropriate at this time | The requirement will not be planned for delivery at this time. Instead it will either: - reconsidered for inclusion in a later project / phase, OR - be dropped completely

## Effort Estimate Guidelines
Technical Analysis - Effort Estimate Guidelines
Effort Estimate | Approx. number of development days
Small | Up to 5 days
Medium | 6 to 10 days
Large | 11 to 20 days
Extra Large | More than 20+ days